## pro1
Sapiri gamak - people's participatory Rural development progrmme - 2020
Physical and financial progress of the dec 31
Ds division - Ipalogama
No | name of projects | GN division | sector | length(km/m) | allocation (Rs) | implementing agency | name of contractor/society) | progress | [11 empty] | no of beneficiaries | Bills in hand
[8 empty] | finance |  | Physical
[8 empty] | expenditure(Rs.Mn) | % | A | B |  |  |  | C | D | E | F | G
[11 empty] | B1 | B2 | B3 | B4
1 | Road development - near the Buddha shrine upto Mr. shelton's house inter locked road in Walawwegama | Walawwegama | RA | 44.5m | 495000 | P.sabawa | Gamunu govi-meegassagama | 494996.65 | 100% | [9 empty] | 1 | 175
2 | Road development - from Mr.J.A. Nimal premasiri's house upto J.A.Upali jayasinghe's house in Kanakkanmaduwa | Walawwegama | RA | 50m | 495000 | P.sabawa | Gamunu govi-meegassagama | 494770.43 | 100% | [9 empty] | 1 | 45
3 | Road development -from Rajapaksha's house upto the road | Walawwegama | RA | 82.2m | 990000 | P.sabawa | suwa udana praiamula-gonapthirawa | 989997.87 | 100% | [9 empty] | 1 | 450
4 | Construction a self employment training center in palugaswewa school (reserved place) | Palugaswewa govipola | OI | 1 | 1980000 | A.G.A.office | samagi govi sanvidaaya - palogaswewa | 1980000 | 100% | [9 empty] | 1 | 1880
5 | Construction the Retaining wall of D 2 canel from Lama ethana achchi's house upto Mr. fareek's house in Kalawewa | Kalawewa | MI | 87m | 1980000 | Mahaweli | kalawewa govi sanvidanaya | 1935156.8 | 100% | [9 empty] | 1 | 1100
6 | Road development - near Mr. B.M. Rifai's house up to the forward of akkara 06 road in Kappalgama | Kusalanagama | RA | 84m | 990000 | Mahaweli | warenthu kotuwa govi sanvidanaya | 979739.57 | 100% | [9 empty] | 1 | 500
7 | Road development - near Mr.Faric's house up to the forward of the road in wali Akkaraya | Kusalanagama | RA | 70m | 990000 | P.sabawa | warenthu kotuwa govi sanvidanaya | 988994.45 | 100% | [9 empty] | 1 | 500
8 | Road development from Mr.Amaranaden's house up to Mr.Sakariya's house in Theliyawa | Amunuwatiya | RA | 84m | 990000 | P.sabawa | Gamunu govi-meegassagama | 989742.87 | 100% | [9 empty] | 1 | 30
9 | Road development near the Alahappreumagama transfomer road | Amunuwatiya | RA | 57.7m | 990000 | P.sabawa | warenthu kotuwa govi sanvidanaya | [10 empty] | 1 |  | 40 | 988602.77
10 | Road development - Anumathi tank dam road in Vijithapura | Vijirthapura | RA | 40.5m | 495000 | P.sabawa | Gamunu govi-meegassagama | 492795.57 | 100% | [9 empty] | 1 | 300
11 | Road development - Anumathi tank dam road in Vijithapura | Vijirthapura | RA | 81.8m | 990000 | P.sabawa | suwa udana praiamula-gonapthirawa | 985641.28 | 100% | [9 empty] | 1 | 300
12 | Road development from Mr.chaminda's house upto Mr.Amith's house in fishing village - Vijithapura | Vijirthapura | RA | 43m | 495000 | P.sabawa | iaplogama wadihiti sanvidanaya | 490991.75 | 100% | [9 empty] | 1 | 100
13 | Road development from Thilakarathne's house upto Vijepala's house in Amanakkattuwa | Amanakkattuwa | RA | 81.8m | 990000 | P.sabawa | dathusena govi sanvidanaya | 989800 | 100% | [9 empty] | 1 | 520
14 | Renovation the community hall as a self employment training center in Amanakkattuwa | Amanakkattuwa | OI | 1 | 990000 | A.G.A.office | dathusena govi sanvidanaya | 990000 | 100% | [9 empty] | 1 | 80
15 | Construction the Retaining wall in ottoru canel in 2 nd Palugaswewa | Akkara 500 | MI | 23.5m | 495000 | Mahaweli | ottoru ela govi - kalakarabewa | 483828.44 | 100% | [9 empty] | 1 | 500
16 | Road development of karabeeewa - kaduruweegama road in Kaduruweegama | Akkara 500 | RA | 82 m | 990000 | P.sabawa | ottoru ela govi - kalakarabewa | 989746.37 | 100% | [9 empty] | 1 | 1000
17 | Renovation the S.M. chandrasena auditorium hall as a self employment training center in 2 nd Palugaswewa | Akkara 500 | OI | 1 | 495000 | A.G.A.office | ottoru ela govi - kalakarabewa | 473060.05 | 100% | [9 empty] | 1 | 250
18 | Road development from the boo tree in kagama 4th canel upto inter locked road | Kagama | RA | 91m | 1188000 | P.sabawa | siriliya kantha - aluth ganthiriyagama | 1185959.36 | 100% | [9 empty] | 1 | 550
19 | Road development from Mr. nandasena's house (inter locked ) upto mada kotasa - kallanchiyagama main road in 3 ela | Kagama | RA | 46.5m | 792000 | P.sabawa | siriliya kantha - aluth ganthiriyagama | 781992.58 | 100% | [9 empty] | 1 | 550
20 | Construction a self employment training center in sri abhaya raja temple's land in 6 ela | R.B.2 Kagama | OI | 1 | 1980000 | A.G.A.office | dathusena govi sanvidanaya | 1979950 | 100% | [9 empty] | 1 | 1300
21 | Development of the udeni pura access road | Sangattawa | RA | 620m | 495000 | P.sabawa | samagi govi sanvidaaya - palogaswewa | 494995.2 | 100% | [9 empty] | 1 | 150
22 | Construction a self employment training center in Sangattawa village | Sangattawa | OI | 1 | 495000 | A.G.A.office | samagi govi sanvidanaya' | 495000 | 100% | [9 empty] | 1 | 200
23 | By Roads development from in Sirikkulama | Sangattawa | RA | 203m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | [10 empty] | 1 |  | 80 | 492694.6
24 | Road development from Mr.H.P.sugathadasa's house upto Mr.Rathnasiri's house road in Sirikkulama | Sangattawa | RA | 605m | 495000 | P.sabawa | samagi govi sanvidanaya' | 494982.45 | 100% | [9 empty] | 1 | 50
25 | Road development in Bangalakotuwa village | Sangattawa | RA | 597m | 495000 | P.sabawa | suwa shakthi kantha samithiya | [10 empty] | 1 |  | 1000 | 490070.28
26 | Road development from manju's shop upto Mr.Ghanathilaka's land in Akkara 100 | Mahailuppalama | RA | 675m | 495000 | P.sabawa | elder society - ipalogama | 435946.32 | 100% | [9 empty] | 1 | 75
27 | Road development in front of Funeral center road in LB 2 | Mahailuppalama | RA |  | 495000 | P.sabawa |  | 494982.71 | 100% | [9 empty] | 1 | 75
28 | Development the sanitary facilities in Mahailuppallama school | Mahailuppalama | SF | toilet 2 | 495000 | Education | pasal sanvardana samithiya | 495000 | 100% | [9 empty] | 1 | 700
29 | Road development from P. Somapala's house upto J.L.Jayakody's house in L.B.7 Canal road in dikwewa | Dikwewa | RA | 560m | 495000 | P.sabawa | samagi govi sanvidanaya' | 494965.27 | 100% | [9 empty] | 1 | 450
30 | Road development from Road development from Mr.Rohitha's shop upto Mr.Ghunasinghe's house in dikwewa | Dikwewa | RA | 760m | 495000 | P.sabawa | samagi govi sanvidanaya' | [10 empty] | 1 |  | 150 | 494995.53
31 | Road development from Mr.Dimuthu's house upto Mr.Amali's house in track 4 | Dikwewa | RA | 647m | 495000 | P.sabawa | samagi govi sanvidanaya' | 494918.25 | 100% | [9 empty] | 1 | 250
32 | Road development from Mrs. Anulawathi's house upto Mr.wanninayake's house in track 4 | Dikwewa | RA | 700m | 495000 | Mahaweli | samagi govi sanvidanaya' | [10 empty] | 1 |  | 120 | 494900
33 | Renovation the community hall as a self employment training center in nelliyagama | Ipalogama | OI | 1 | 495000 | A.G.A.office | ipalogama govi sanvidanaya | 495000 | 100% | [9 empty] | 1 | 200
34 | Road development from near Mr.Madduma bandara's house upto Mr.ruwan's house in ipalogama | Ipalogama | RA | 620m | 495000 | P.sabawa | sinhayage sanvidanaya | 494964.91 | 100% | [9 empty] | 1 | 500
35 | Road development from Mr. Palihta's house upto the road in Gamini halmillawa village road | Ipalogama | RA | 1100m | 990000 | P.sabawa | sinhayage sanvidanaya | [10 empty] | 1 |  | 1500 | 971645.67
36 | Renovation the community hall as a self employment training center in Manewa | Manewa | OI | 1 | 495000 | A.G.A.office | mahanama govi sanvidanaya | 495000 | [10 empty] | 1 | 222
37 | Road development from Mr.Naleen's house upto meegaha akkaraya road Manewa | Manewa | RA | 214m | 495000 | P.sabawa | mahanama govi sanvidanaya | [10 empty] | 1 |  | 222 | 441620.48
38 | Development of the Machchagama temple road | Manewa | RA | 540m | 495000 | P.sabawa | amane govi sanvidanaya | [10 empty] | 1 |  | 89 | 490099.74
39 | Road development from Amane village upto Swasthigama road in Amane | Manewa | RA | 940m | 495000 | P.sabawa | amane govi sanvidanaya | [10 empty] | 1 |  | 22 | 490064.26
40 | Road development - near the Mr. Allepola's house in Ganthiriyagama | Ganthiriyagama | RA | 150 m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | [10 empty] | 1 |  | 800 | 465916.19
41 | Road development - from Mr.Gamini's house upto theroad in Ganthiriyagama | Ganthiriyagama | RA | 218m | 495000 | P.sabawa | ganthiriyagana govi sanvidanaya | [10 empty] | 1 |  | 500 | 494995.07
42 | Road development - near the sudarmarama temple upto ganthiriyagama village road | Ganthiriyagama | RA | 620m | 495000 | P.sabawa | samagi govi-kudameegassagama | 494995.21 | 100% | [9 empty] | 1 | 250
43 | Road development from school land upto parana yoda ela road in pahalawembuwa | Ganthiriyagama | RA | 740m | 495000 | P.sabawa | samagi govi-kudameegassagama | 494988.35 | 100% | [9 empty] | 1 | 150
44 | Road development - near Mr.upul's house road in track 2 | Senapura | RA | 78m | 990000 | P.sabawa | mahasen govi sanvidanaya | 989744.66 | 100% | [9 empty] | 1 | 350
45 | Renovation the community hallas a self employment training center in senapura town, | Senapura | OI | 1 | 990000 | A.G.A.office | mahasen govi sanvidanaya | [10 empty] | 1 |  | 500 | 990000
46 | Road development infront of the pre school road in Narangallegama | Narangallegama | RA | 35m | 495000 | P.sabawa | senalooka govi sanvidanaya | 494634.9 | 100% | [9 empty] | 1 | 400
47 | Road development from Mr. Niyas's house upto Koin manike's house road in Narangallegama | Narangallegama | RA | 79m | 990000 | P.sabawa | senalooka govi sanvidanaya | 989770.9 | 100% | [9 empty] | 1 | 600
48 | Road development infront of the pre school road in Narangallegama | Narangallegama | RA | 34.5m | 495000 | P.sabawa | senalooka govi sanvidanaya | [10 empty] | 1 |  | 100 | 494634.9
49 | Agri Road development from kalakarabewa 1 st sluice upto akkara 08 in Kalakarabewa | Aswadduma | RA | 440m | 495000 | Mahaweli | dathusena govi sanvidanaya | 493773.33 | 100% | [9 empty] | 1 | 100
50 | Agri Road development from kalakarabewa 2 st sluice upto pahala 13 in kalakarabewa | Aswadduma | RA | 410m | 495000 | Mahaweli | dathusena govi sanvidanaya | [10 empty] | 1 |  | 60 | 493652.69
51 | Road development from Mr.susantha adikari's house upto Mr.Raveendra wadikkara's house in kagama parana badhu idama | Aswadduma | RA | 680m | 495000 | P.sabawa | pragathi eksath govi sanvidanaya | 494995.2 | 100% | [9 empty] | 1 | 550
52 | Road development from Mr.sisira kumara's house upto Mr.D.M.bandaranayake's house in samurdhi mawatha in Kagama parana badhu idama | Aswadduma | RA | 40.8 | 495000 | P.sabawa | pragathi eksath govi sanvidanaya | 494991.19 | 100% | [9 empty] | 1 | 300
53 | Road development in galwanguwa - aluth ganthiriyagama main road in Galwanguwa | Galwanguwa | RA | 91m | 1485000 | P.sabawa | samupakara samitya-ipalogama | 1482491.74 | 100% | [9 empty] | 1 | 1800
54 | Road development Of Mee malgama - wedinigama road | Galwanguwa | RA | 675m | 495000 | P.sabawa | siriliya kantha - aluth ganthiriyagama | [10 empty] | 1 |  | 800 | 495000
55 | Road development from A.G.M.gunasekara's house upto D.13 canal | Kallanchiyagama | RA | 650m | 495000 | P.sabawa | sri agrabodhi govi sanvidanaya | [10 empty] | 1 |  | 50 | 494690.62
56 | Development of the akkara 30 road from near the kallanchiyagama spill upto kagama - gonapathirawa road in 1 dennawa | Kallanchiyagama | RA | 700m | 495000 | P.sabawa | siriliya kantha - aluth ganthiriyagama | [10 empty] | 1 |  | 650 | 490084.63
57 | Road development from Mr.Pattrick's house upto Meemalgama road | Kallanchiyagama | RA | 1300m | 990000 | P.sabawa | siriliya kantha - aluth ganthiriyagama | [10 empty] | 1 |  | 250 | 953560.95
58 | Road development from senapura road upto Mr.W.G.dayarathne's house in Kuda Meegassagama | Gonapathirawa | RA | 41.5m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | 494781.38 | 100% | [9 empty] | 1 | 60
59 | Road development from kudameegassagama tank road | Gonapathirawa | RA | 40.4m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | 494687.31 | 100% | [9 empty] | 1 | 250
60 | Road development from near Mahameegassagama cemetery road | Gonapathirawa | RA | 38.5m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | 494981.05 | 100% | [9 empty] | 1 | 60
61 | Road development - Mahameegassagama orphen road | Gonapathirawa | RA | 45m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | 492359.27 | 100% | [9 empty] | 1 | 200
62 | Road development from kadiyangalla main road upto Mr.Gamini weeragama's house in Kaadiyangalla | Kadiyangalla | RA | 560m | 495000 | P.sabawa | ekamuthu govi sanvidanaya | [10 empty] | 1 |  | 35 | 392968.41
63 | Road development from kadiyangalla uda gammanaya upto Mr.Prabath chinthaka's house in Kadiyangalle | Kadiyangalla | RA | 1 | 495000 | P.sabawa | dathusena govi sanvidanaya | 495000 | 100% | [9 empty] | 1 | 20
64 | By Road development from mr. Ranasinghe's house upto yodha ela river road in govipola | Kadiyangalla | RA | 230m | 495000 | P.sabawa | ekamuthu govi sanvidanaya | [10 empty] | 1 |  | 200 | 304091.72
65 | Road development from gonapathirawa water tank road upto Mr. Nalaka's house in Gonapathirawa | Kadiyangalla | RA | 550m | 495000 | P.sabawa | ekamuthu govi sanvidanaya | [10 empty] | 1 |  | 50 | 455188.57
66 | Road development - from akkara 28 inter locked road upto the Wedinigama | Wedinigama | RA | 116m | 1485000 | P.sabawa | ipalogama wadihiti sanvidanaya | [10 empty] | 1 |  | 1500 | 1472780.46
67 | Road development - near MR.Jagath's house road in Mihidhugama | Wedinigama | RA | 205m | 495000 | P.sabawa | sri agrabodhi govi sanvidanaya | [10 empty] | 1 |  | 800 | 486740.61
68 | Road development - near the Aluvihareegama GN .Office road | Galagedaragama | RA | 320m | 495000 | P.sabawa | ekamuthu govi sanvidanaya | [10 empty] | 1 |  | 200 | 475027.78
69 | Road development from Mr.I.M.dayarathe's house (380km) road and Mr.R.M. Appuhami's house - S.M.wipulasena's faddy in aluviharegama | Galagedaragama | RA | 647m | 495000 | Mahaweli | sri wanasingha govi sanvidanaya | [10 empty] | 1 |  | 300 | 485786.3
70 | Road development in galagrdaragama gama mada para | Galagedaragama | RA | 79.5m | 990000 | P.sabawa | ekamuthu govi sanvidanaya | 989744.66 | 100% | [9 empty] | 1 | 100
71 | Road development - tank road in aluth dabewatana | Aluth dabewatana | RA | 81m | 990000 | P.sabawa | dathusena govi sanvidanaya | 989615.86 | 100% | [9 empty] | 1 | 150
72 | Road development from aluth dabeewatana 2 nd community hall upto palliya koutwa road | Aluth dabewatana | RA | 77m | 990000 | P.sabawa | dathusena govi sanvidanaya | 988945.21 | 100% | [9 empty] | 1 | 130
73 | Construction the canal streams of mahagalagama tank in Pallekagama | Kunchikulama | RA | 1 | 495000 | P.sabawa | gajaba govi sanvidanaya | 491101.53 | 100% | [9 empty] | 1 | 150
74 | Development of the Ranajayapura cemetery road | Kunchikulama | RA | 46m | 495000 | P.sabawa | parakumba govi sanvidanaya | [10 empty] | 1 |  | 1800 | 324740.17
75 | Development of the kunchikulama tank spill - canal (kunchkulama mini muthu pre school road - near shantha siri adikari house ) | Kunchikulama | RA | 1 | 495000 | P.sabawa | Gamunu govi-meegassagama | [10 empty] | 1 |  | 50 | 447959.78
76 | Road development from near Mis.Rasika athlathmudali's house upto Gamunupura road | Kunchikulama | RA | 357m | 495000 | P.sabawa | gajaba govi sanvidanaya | [10 empty] | 1 |  | 70 | 494991.21
77 | Development of Thilakapura -Mailagasewa road | Hiripitiyagama | RA | 900m | 495000 | P.sabawa | sri agrabodhi govi sanvidanaya | [10 empty] | 1 |  | 500 | 489568.27
78 | Road development infront of the Mr.pradeep's house in pin para | Hiripitiyagama | RA | 417m | 495000 | P.sabawa | vijitha govi sanvidanaya | [10 empty] | 1 |  | 500 | 398057.4
79 | Road development from eductional office upto Heen yaya road in Hiripitiyagama | Hiripitiyagama | RA | 270m | 495000 | P.sabawa | vijitha govi sanvidanaya | [10 empty] | 1 |  | 500 | 494329.14
80 | Development of the Viveen road in Hiripitiyagama | Hiripitiyagama | RA | 40m | 495000 | P.sabawa | vijitha govi sanvidanaya | 494979.85 | 100% | [9 empty] | 1 | 500
81 | Road development from Puliyankulama pin para upto Kalupalama road | Puliyankulama | RA | 546m | 495000 | P.sabawa | ipalogama wadihiti sanvidanaya | [10 empty] | 1 |  | 500 | 403902.39
82 | ByRoad development from E.M.darmasena's house upto the road puliyankulama | Puliyankulama | RA | 206m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | [10 empty] | 1 |  | 600 | 403706.83
83 | Road development from pugollagama community hall upto yoda ela road in Pugollagama | Puliyankulama | RA | 198m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | [10 empty] | 1 |  | 600 | 366805.27
84 | Road development from aluth puliyankulama cemetery road upto Mr.Ranjith's house in Pugollagama | Puliyankulama | RA | 210m | 495000 | P.sabawa | sri agrabodhi govi sanvidanaya | [10 empty] | 1 |  | 300 | 461188.58
85 | Development of Indunugala -kahatagaha road | Dampalassagama | MI | 700m | 495000 | P.sabawa | parakumba govi sanvidanaya | 494999.6 | 100% | [9 empty] | 1 | 750
86 | development the health center in Dampalassagama | Dampalassagama | OT | 1 | 495000 | P.sabawa | parakumba govi sanvidanaya | 495000 | 100% | [9 empty] | 1 | 1500
87 | Road development of dampalassagama - dammasheelarama road | Dampalassagama | RA | 200m | 495000 | P.sabawa | parakum govi sanvidanaya | [10 empty] | 1 |  | 500 | 451851.82
88 | Development the spill of Matangamauwa tank | Dampalassagama | RA | 1 | 495000 | palath wari | parakumba govi sanvidanaya | 489539.12 | 100% | [9 empty] | 1 | 500
89 | Road development from hapidiyagama community hall upto hapidiyagama village | Dampalassagama | RA | 80.2m | 990000 | P.sabawa | suhada govi-hapidiyagama | 969301.96 | 100% | [9 empty] | 1 | 170
90 | Development of the Settikulama - Hapidiyagama road | Henukwegama | RA | 69.3m | 990000 | P.sabawa | suhada govi-hapidiyagama | 910975.29 | 100% | [9 empty] | 1 | 280
91 | Development of the Budugekanda temple road in Ihalakagama | Ihalakagama | RA | 85m | 1089000 | P.sabawa | nawarella govi-ihalakagama | 925455.96 | 100% | [9 empty] | 1 | 750
92 | Development of Bogahalanda Agri road in Ihalakagama | Ihalakagama | RA | 1000m | 891000 | P.sabawa | nawarella govi-ihalakagama | 888100 | 100% | [9 empty] | 1 | 500
93 |  |  |  |  | 63360000 |  |  | 42112872.68 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 56 | 39510 | 19536913.09
මාසික වාර්තාව - මුදල් අමාත්‍යාංශය
සෑම මසකමඅවසානයේ ඊලග සම 10 දිනට පෙර යැවීම

## ෙගවූ බිල්
Sapiri gamak - people's participatory Rural development progrmme - 2020
Physical and financial progress of the dec 31
Ds division - Ipalogama |  |  |  |  | ෙගවූ බිල් පත් වටිනාකම්
No | name of projects | GN division | sector | length(km/m) | allocation (Rs) | implementing agency | name of contractor/society) | progress | [11 empty] | no of beneficiaries
[8 empty] | finance |  | Physical
[8 empty] | expenditure(Rs.Mn) | % | A | B |  |  |  | C | D | E | F | G
[11 empty] | B1 | B2 | B3 | B4
1 | Road development - near the Buddha shrine upto Mr. shelton's house inter locked road in Walawwegama | Walawwegama | RA | 44.5m | 495000 | P.sabawa | Gamunu govi-meegassagama | 494996.65 | 100% | [9 empty] | 1 | 175
2 | Road development - from Mr.J.A. Nimal premasiri's house upto J.A.Upali jayasinghe's house in Kanakkanmaduwa | Walawwegama | RA | 50m | 495000 | P.sabawa | Gamunu govi-meegassagama | 494770.43 | 100% | [9 empty] | 1 | 45
3 | Road development -from Rajapaksha's house upto the road | Walawwegama | RA | 82.2m | 990000 | P.sabawa | suwa udana praiamula-gonapthirawa | 989997.87 | 100% | [9 empty] | 1 | 450
4 | Construction a self employment training center in palugaswewa school (reserved place) | Palugaswewa govipola | OI | 1 | 1980000 | A.G.A.office | samagi govi sanvidaaya - palogaswewa | 1980000 | 100% | [9 empty] | 1 | 1880
5 | Construction the Retaining wall of D 2 canel from Lama ethana achchi's house upto Mr. fareek's house in Kalawewa | Kalawewa | MI | 87m | 1980000 | Mahaweli | kalawewa govi sanvidanaya | 1935156.8 | 100% | [9 empty] | 1 | 1100
6 | Road development - near Mr. B.M. Rifai's house up to the forward of akkara 06 road in Kappalgama | Kusalanagama | RA | 84m | 990000 | Mahaweli | warenthu kotuwa govi sanvidanaya | 979739.57 | 100% | [9 empty] | 1 | 500
7 | Road development - near Mr.Faric's house up to the forward of the road in wali Akkaraya | Kusalanagama | RA | 70m | 990000 | P.sabawa | warenthu kotuwa govi sanvidanaya | 988994.45 | 100% | [9 empty] | 1 | 500
8 | Road development from Mr.Amaranaden's house up to Mr.Sakariya's house in Theliyawa | Amunuwatiya | RA | 84m | 990000 | P.sabawa | Gamunu govi-meegassagama | 989742.87 | 100% | [9 empty] | 1 | 30
9 | Road development - Anumathi tank dam road in Vijithapura | Vijirthapura | RA | 40.5m | 495000 | P.sabawa | Gamunu govi-meegassagama | 492795.57 | 100% | [9 empty] | 1 | 300
10 | Road development - Anumathi tank dam road in Vijithapura | Vijirthapura | RA | 81.8m | 990000 | P.sabawa | suwa udana praiamula-gonapthirawa | 985641.28 | 100% | [9 empty] | 1 | 300
11 | Road development from Mr.chaminda's house upto Mr.Amith's house in fishing village - Vijithapura | Vijirthapura | RA | 43m | 495000 | P.sabawa | iaplogama wadihiti sanvidanaya | 490991.75 | 100% | [9 empty] | 1 | 100
12 | Road development from Thilakarathne's house upto Vijepala's house in Amanakkattuwa | Amanakkattuwa | RA | 81.8m | 990000 | P.sabawa | dathusena govi sanvidanaya | 989800 | 100% | [9 empty] | 1 | 520
13 | Renovation the community hall as a self employment training center in Amanakkattuwa | Amanakkattuwa | OI | 1 | 990000 | A.G.A.office | dathusena govi sanvidanaya | 990000 | 100% | [9 empty] | 1 | 80
14 | Construction the Retaining wall in ottoru canel in 2 nd Palugaswewa | Akkara 500 | MI | 23.5m | 495000 | Mahaweli | ottoru ela govi - kalakarabewa | 483828.44 | 100% | [9 empty] | 1 | 500
15 | Road development of karabeeewa - kaduruweegama road in Kaduruweegama | Akkara 500 | RA | 82 m | 990000 | P.sabawa | ottoru ela govi - kalakarabewa | 989746.37 | 100% | [9 empty] | 1 | 1000
16 | Renovation the S.M. chandrasena auditorium hall as a self employment training center in 2 nd Palugaswewa | Akkara 500 | OI | 1 | 495000 | A.G.A.office | ottoru ela govi - kalakarabewa | 473060.05 | 100% | [9 empty] | 1 | 250
17 | Road development from the boo tree in kagama 4th canel upto inter locked road | Kagama | RA | 91m | 1188000 | P.sabawa | siriliya kantha - aluth ganthiriyagama | 1185959.36 | 100% | [9 empty] | 1 | 550
18 | Road development from Mr. nandasena's house (inter locked ) upto mada kotasa - kallanchiyagama main road in 3 ela | Kagama | RA | 46.5m | 792000 | P.sabawa | siriliya kantha - aluth ganthiriyagama | 781992.58 | 100% | [9 empty] | 1 | 550
19 | Construction a self employment training center in sri abhaya raja temple's land in 6 ela | R.B.2 Kagama | OI | 1 | 1980000 | A.G.A.office | dathusena govi sanvidanaya | 1979950 | 100% | [9 empty] | 1 | 1300
20 | Development of the udeni pura access road | Sangattawa | RA | 620m | 495000 | P.sabawa | samagi govi sanvidaaya - palogaswewa | 494995.2 | 100% | [9 empty] | 1 | 150
21 | Construction a self employment training center in Sangattawa village | Sangattawa | OI | 1 | 495000 | A.G.A.office | samagi govi sanvidanaya' | 495000 | 100% | [9 empty] | 1 | 200
22 | Road development from Mr.H.P.sugathadasa's house upto Mr.Rathnasiri's house road in Sirikkulama | Sangattawa | RA | 605m | 495000 | P.sabawa | samagi govi sanvidanaya' | 494982.45 | 100% | [9 empty] | 1 | 50
23 | Road development from manju's shop upto Mr.Ghanathilaka's land in Akkara 100 | Mahailuppalama | RA | 675m | 495000 | P.sabawa | elder society - ipalogama | 435946.32 | 100% | [9 empty] | 1 | 75
24 | Road development in front of Funeral center road in LB 2 | Mahailuppalama | RA |  | 495000 | P.sabawa |  | 494982.71 | 100% | [9 empty] | 1 | 75
25 | Development the sanitary facilities in Mahailuppallama school | Mahailuppalama | SF | toilet 2 | 495000 | Education | pasal sanvardana samithiya | 495000 | 100% | [9 empty] | 1 | 700
26 | Road development from P. Somapala's house upto J.L.Jayakody's house in L.B.7 Canal road in dikwewa | Dikwewa | RA | 560m | 495000 | P.sabawa | samagi govi sanvidanaya' | 494965.27 | 100% | [9 empty] | 1 | 450
27 | Road development from Mr.Dimuthu's house upto Mr.Amali's house in track 4 | Dikwewa | RA | 647m | 495000 | P.sabawa | samagi govi sanvidanaya' | 494918.25 | 100% | [9 empty] | 1 | 250
28 | Renovation the community hall as a self employment training center in nelliyagama | Ipalogama | OI | 1 | 495000 | A.G.A.office | ipalogama govi sanvidanaya | 495000 | 100% | [9 empty] | 1 | 200
29 | Road development from near Mr.Madduma bandara's house upto Mr.ruwan's house in ipalogama | Ipalogama | RA | 620m | 495000 | P.sabawa | sinhayage sanvidanaya | 494964.91 | 100% | [9 empty] | 1 | 500
30 | Renovation the community hall as a self employment training center in Manewa | Manewa | OI | 1 | 495000 | A.G.A.office | mahanama govi sanvidanaya | 495000 | [10 empty] | 1 | 222
31 | Road development - near the sudarmarama temple upto ganthiriyagama village road | Ganthiriyagama | RA | 620m | 495000 | P.sabawa | samagi govi-kudameegassagama | 494995.21 | 100% | [9 empty] | 1 | 250
32 | Road development from school land upto parana yoda ela road in pahalawembuwa | Ganthiriyagama | RA | 740m | 495000 | P.sabawa | samagi govi-kudameegassagama | 494988.35 | 100% | [9 empty] | 1 | 150
33 | Road development - near Mr.upul's house road in track 2 | Senapura | RA | 78m | 990000 | P.sabawa | mahasen govi sanvidanaya | 989744.66 | 100% | [9 empty] | 1 | 350
34 | Road development infront of the pre school road in Narangallegama | Narangallegama | RA | 35m | 495000 | P.sabawa | senalooka govi sanvidanaya | 494634.9 | 100% | [9 empty] | 1 | 400
35 | Road development from Mr. Niyas's house upto Koin manike's house road in Narangallegama | Narangallegama | RA | 79m | 990000 | P.sabawa | senalooka govi sanvidanaya | 989770.9 | 100% | [9 empty] | 1 | 600
36 | Agri Road development from kalakarabewa 1 st sluice upto akkara 08 in Kalakarabewa | Aswadduma | RA | 440m | 495000 | Mahaweli | dathusena govi sanvidanaya | 493773.33 | 100% | [9 empty] | 1 | 100
37 | Road development from Mr.susantha adikari's house upto Mr.Raveendra wadikkara's house in kagama parana badhu idama | Aswadduma | RA | 680m | 495000 | P.sabawa | pragathi eksath govi sanvidanaya | 494995.2 | 100% | [9 empty] | 1 | 550
38 | Road development from Mr.sisira kumara's house upto Mr.D.M.bandaranayake's house in samurdhi mawatha in Kagama parana badhu idama | Aswadduma | RA | 40.8 | 495000 | P.sabawa | pragathi eksath govi sanvidanaya | 494991.19 | 100% | [9 empty] | 1 | 300
39 | Road development in galwanguwa - aluth ganthiriyagama main road in Galwanguwa | Galwanguwa | RA | 91m | 1485000 | P.sabawa | samupakara samitya-ipalogama | 1482491.74 | 100% | [9 empty] | 1 | 1800
40 | Road development from senapura road upto Mr.W.G.dayarathne's house in Kuda Meegassagama | Gonapathirawa | RA | 41.5m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | 494781.38 | 100% | [9 empty] | 1 | 60
41 | Road development from kudameegassagama tank road | Gonapathirawa | RA | 40.4m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | 494687.31 | 100% | [9 empty] | 1 | 250
42 | Road development from near Mahameegassagama cemetery road | Gonapathirawa | RA | 38.5m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | 494981.05 | 100% | [9 empty] | 1 | 60
43 | Road development - Mahameegassagama orphen road | Gonapathirawa | RA | 45m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | 492359.27 | 100% | [9 empty] | 1 | 200
44 | Road development from kadiyangalla uda gammanaya upto Mr.Prabath chinthaka's house in Kadiyangalle | Kadiyangalla | RA | 1 | 495000 | P.sabawa | dathusena govi sanvidanaya | 495000 | 100% | [9 empty] | 1 | 20
45 | Road development in galagrdaragama gama mada para | Galagedaragama | RA | 79.5m | 990000 | P.sabawa | ekamuthu govi sanvidanaya | 989744.66 | 100% | [9 empty] | 1 | 100
46 | Road development - tank road in aluth dabewatana | Aluth dabewatana | RA | 81m | 990000 | P.sabawa | dathusena govi sanvidanaya | 989615.86 | 100% | [9 empty] | 1 | 150
47 | Road development from aluth dabeewatana 2 nd community hall upto palliya koutwa road | Aluth dabewatana | RA | 77m | 990000 | P.sabawa | dathusena govi sanvidanaya | 988945.21 | 100% | [9 empty] | 1 | 130
48 | Construction the canal streams of mahagalagama tank in Pallekagama | Kunchikulama | RA | 1 | 495000 | P.sabawa | gajaba govi sanvidanaya | 491101.53 | 100% | [9 empty] | 1 | 150
49 | Development of the Viveen road in Hiripitiyagama | Hiripitiyagama | RA | 40m | 495000 | P.sabawa | vijitha govi sanvidanaya | 494979.85 | 100% | [9 empty] | 1 | 500
50 | Development of Indunugala -kahatagaha road | Dampalassagama | MI | 700m | 495000 | P.sabawa | parakumba govi sanvidanaya | 494999.6 | 100% | [9 empty] | 1 | 750
51 | development the health center in Dampalassagama | Dampalassagama | OT | 1 | 495000 | P.sabawa | parakumba govi sanvidanaya | 495000 | 100% | [9 empty] | 1 | 1500
52 | Development the spill of Matangamauwa tank | Dampalassagama | RA | 1 | 495000 | palath wari | parakumba govi sanvidanaya | 489539.12 | 100% | [9 empty] | 1 | 500
53 | Road development from hapidiyagama community hall upto hapidiyagama village | Dampalassagama | RA | 80.2m | 990000 | P.sabawa | suhada govi-hapidiyagama | 969301.96 | 100% | [9 empty] | 1 | 170
54 | Development of the Settikulama - Hapidiyagama road | Henukwegama | RA | 69.3m | 990000 | P.sabawa | suhada govi-hapidiyagama | 910975.29 | 100% | [9 empty] | 1 | 280
55 | Development of the Budugekanda temple road in Ihalakagama | Ihalakagama | RA | 85m | 1089000 | P.sabawa | nawarella govi-ihalakagama | 925455.96 | 100% | [9 empty] | 1 | 750
56 | Development of Bogahalanda Agri road in Ihalakagama | Ihalakagama | RA | 1000m | 891000 | P.sabawa | nawarella govi-ihalakagama | 888100 | 100% | [9 empty] | 1 | 500
[5 empty] | 42570000 |  |  | 42112872.68 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 23572
| උප ඒකතුව රු. | 42112872.68
| පරිපාලන වියදම රු. | 252677.23
| වියදම | 42365549.91

## අතැති බිල්
Sapiri gamak - people's participatory Rural development progrmme - 2020
Physical and financial progress of the dec 31
Ds division - Ipalogama |  |  |  |  | bills in hand | [15 empty] | bills in hand
No | name of projects | GN division | sector | length(km/m) | allocation (Rs) | implementing agency | name of contractor/society) | progress | [11 empty] | no of beneficiaries | Bills in hand
[8 empty] | finance |  | Physical
[8 empty] | expenditure(Rs.Mn) | % | A | B |  |  |  | C | D | E | F | G
[11 empty] | B1 | B2 | B3 | B4
1 | Road development near the Alahappreumagama transfomer road | Amunuwatiya | RA | 57.7m | 990000 | P.sabawa | warenthu kotuwa govi sanvidanaya | [10 empty] | 1 |  | 40 | 988602.77
2 | By Roads development from in Sirikkulama | Sangattawa | RA | 203m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | [10 empty] | 1 |  | 80 | 492694.6
3 | Road development in Bangalakotuwa village | Sangattawa | RA | 597m | 495000 | P.sabawa | suwa shakthi kantha samithiya | [10 empty] | 1 |  | 1000 | 490070.28
4 | Road development from Road development from Mr.Rohitha's shop upto Mr.Ghunasinghe's house in dikwewa | Dikwewa | RA | 760m | 495000 | P.sabawa | samagi govi sanvidanaya' | [10 empty] | 1 |  | 150 | 494995.53
5 | Road development from Mrs. Anulawathi's house upto Mr.wanninayake's house in track 4 | Dikwewa | RA | 700m | 495000 | Mahaweli | samagi govi sanvidanaya' | [10 empty] | 1 |  | 120 | 494900
6 | Road development from Mr. Palihta's house upto the road in Gamini halmillawa village road | Ipalogama | RA | 1100m | 990000 | P.sabawa | sinhayage sanvidanaya | [10 empty] | 1 |  | 1500 | 971645.67
7 | Road development from Mr.Naleen's house upto meegaha akkaraya road Manewa | Manewa | RA | 214m | 495000 | P.sabawa | mahanama govi sanvidanaya | [10 empty] | 1 |  | 222 | 441620.48
8 | Development of the Machchagama temple road | Manewa | RA | 540m | 495000 | P.sabawa | amane govi sanvidanaya | [10 empty] | 1 |  | 89 | 490099.74
9 | Road development from Amane village upto Swasthigama road in Amane | Manewa | RA | 940m | 495000 | P.sabawa | amane govi sanvidanaya | [10 empty] | 1 |  | 22 | 490064.26
10 | Road development - near the Mr. Allepola's house in Ganthiriyagama | Ganthiriyagama | RA | 150 m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | [10 empty] | 1 |  | 800 | 465916.19
11 | Road development - from Mr.Gamini's house upto theroad in Ganthiriyagama | Ganthiriyagama | RA | 218m | 495000 | P.sabawa | ganthiriyagana govi sanvidanaya | [10 empty] | 1 |  | 500 | 494995.07
12 | Renovation the community hallas a self employment training center in senapura town, | Senapura | OI | 1 | 990000 | A.G.A.office | mahasen govi sanvidanaya | [10 empty] | 1 |  | 500 | 990000
13 | Road development infront of the pre school road in Narangallegama | Narangallegama | RA | 34.5m | 495000 | P.sabawa | senalooka govi sanvidanaya | [10 empty] | 1 |  | 100 | 494634.9
14 | Agri Road development from kalakarabewa 2 st sluice upto pahala 13 in kalakarabewa | Aswadduma | RA | 410m | 495000 | Mahaweli | dathusena govi sanvidanaya | [10 empty] | 1 |  | 60 | 493652.69
15 | Road development Of Mee malgama - wedinigama road | Galwanguwa | RA | 675m | 495000 | P.sabawa | siriliya kantha - aluth ganthiriyagama | [10 empty] | 1 |  | 800 | 495000
16 | Road development from A.G.M.gunasekara's house upto D.13 canal | Kallanchiyagama | RA | 650m | 495000 | P.sabawa | sri agrabodhi govi sanvidanaya | [10 empty] | 1 |  | 50 | 494690.62
17 | Development of the akkara 30 road from near the kallanchiyagama spill upto kagama - gonapathirawa road in 1 dennawa | Kallanchiyagama | RA | 700m | 495000 | P.sabawa | siriliya kantha - aluth ganthiriyagama | [10 empty] | 1 |  | 650 | 490084.63
18 | Road development from Mr.Pattrick's house upto Meemalgama road | Kallanchiyagama | RA | 1300m | 990000 | P.sabawa | siriliya kantha - aluth ganthiriyagama | [10 empty] | 1 |  | 250 | 953560.95
19 | Road development from kadiyangalla main road upto Mr.Gamini weeragama's house in Kaadiyangalla | Kadiyangalla | RA | 560m | 495000 | P.sabawa | ekamuthu govi sanvidanaya | [10 empty] | 1 |  | 35 | 392968.41
20 | By Road development from mr. Ranasinghe's house upto yodha ela river road in govipola | Kadiyangalla | RA | 230m | 495000 | P.sabawa | ekamuthu govi sanvidanaya | [10 empty] | 1 |  | 200 | 304091.72
21 | Road development from gonapathirawa water tank road upto Mr. Nalaka's house in Gonapathirawa | Kadiyangalla | RA | 550m | 495000 | P.sabawa | ekamuthu govi sanvidanaya | [10 empty] | 1 |  | 50 | 455188.57
22 | Road development - from akkara 28 inter locked road upto the Wedinigama | Wedinigama | RA | 116m | 1485000 | P.sabawa | ipalogama wadihiti sanvidanaya | [10 empty] | 1 |  | 1500 | 1472780.46
23 | Road development - near MR.Jagath's house road in Mihidhugama | Wedinigama | RA | 205m | 495000 | P.sabawa | sri agrabodhi govi sanvidanaya | [10 empty] | 1 |  | 800 | 486740.61
24 | Road development - near the Aluvihareegama GN .Office road | Galagedaragama | RA | 320m | 495000 | P.sabawa | ekamuthu govi sanvidanaya | [10 empty] | 1 |  | 200 | 475027.78
25 | Road development from Mr.I.M.dayarathe's house (380km) road and Mr.R.M. Appuhami's house - S.M.wipulasena's faddy in aluviharegama | Galagedaragama | RA | 647m | 495000 | Mahaweli | sri wanasingha govi sanvidanaya | [10 empty] | 1 |  | 300 | 485786.3
26 | Development of the Ranajayapura cemetery road | Kunchikulama | RA | 46m | 495000 | P.sabawa | parakumba govi sanvidanaya | [10 empty] | 1 |  | 1800 | 324740.17
27 | Development of the kunchikulama tank spill - canal (kunchkulama mini muthu pre school road - near shantha siri adikari house ) | Kunchikulama | RA | 1 | 495000 | P.sabawa | Gamunu govi-meegassagama | [10 empty] | 1 |  | 50 | 447959.78
28 | Road development from near Mis.Rasika athlathmudali's house upto Gamunupura road | Kunchikulama | RA | 357m | 495000 | P.sabawa | gajaba govi sanvidanaya | [10 empty] | 1 |  | 70 | 494991.21
29 | Development of Thilakapura -Mailagasewa road | Hiripitiyagama | RA | 900m | 495000 | P.sabawa | sri agrabodhi govi sanvidanaya | [10 empty] | 1 |  | 500 | 489568.27
30 | Road development infront of the Mr.pradeep's house in pin para | Hiripitiyagama | RA | 417m | 495000 | P.sabawa | vijitha govi sanvidanaya | [10 empty] | 1 |  | 500 | 398057.4
31 | Road development from eductional office upto Heen yaya road in Hiripitiyagama | Hiripitiyagama | RA | 270m | 495000 | P.sabawa | vijitha govi sanvidanaya | [10 empty] | 1 |  | 500 | 494329.14
32 | Road development from Puliyankulama pin para upto Kalupalama road | Puliyankulama | RA | 546m | 495000 | P.sabawa | ipalogama wadihiti sanvidanaya | [10 empty] | 1 |  | 500 | 403902.39
33 | ByRoad development from E.M.darmasena's house upto the road puliyankulama | Puliyankulama | RA | 206m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | [10 empty] | 1 |  | 600 | 403706.83
34 | Road development from pugollagama community hall upto yoda ela road in Pugollagama | Puliyankulama | RA | 198m | 495000 | P.sabawa | suwa udana praiamula-gonapthirawa | [10 empty] | 1 |  | 600 | 366805.27
35 | Road development from aluth puliyankulama cemetery road upto Mr.Ranjith's house in Pugollagama | Puliyankulama | RA | 210m | 495000 | P.sabawa | sri agrabodhi govi sanvidanaya | [10 empty] | 1 |  | 300 | 461188.58
36 | Road development of dampalassagama - dammasheelarama road | Dampalassagama | RA | 200m | 495000 | P.sabawa | parakum govi sanvidanaya | [10 empty] | 1 |  | 500 | 451851.82
93 |  |  |  |  | 20790000 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 15938 | 19536913.09
| උප ඒකතුව රු. | 19536913.09
| පරිපාලන වියදම රු. | 117221.47
| මුළු වියදම රු. | 19654134.56

## pro2
Sapiri gamak - peples's participatory rural development programme - 2020
2020.12.31
ds division - ipalogama | [30 empty] | බදාදා
NO | projects | [9 empty] | Allocation | [9 empty] | Physical Progress ** (No. of Projects) | [9 empty] | Expenditure (Rs. Mn) | No. of Beneficiaries
| No. of projects approved |  |  | total categorized by sectors | [6 empty] | Approved allocation (Rs Mn) | Total Allocation Categorized by Sectors * | [8 empty] | A | B |  |  |  | C | D | E | F | G
|  | I (RA) | II | III (RE) | IV (MI) | V (WS) | VI (RH) | VII (SD) | VIII | IX (OI) |  | I (RA) | II | III (RE) | IV (MI) | V(WS) | VI (RH) | VII (SD) | VIII | IX (OI) |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
1 | 92 | 77 |  |  | 5 |  | 1 | 1 |  | 8 | 63.36 | 50.51 |  |  | 4 |  | 0.5 | 0.5 |  | 7.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 56 | 42.36 | 39510
සති වාර්තාව - මුදල් අමාත්‍යාංශය - සෑම සතියකම බදාදා දින පෙ.ව.11.00ට පෙර

## Sheet1
ප්‍රාදේශීය ලේකම් කාර්යාලය - ඉපලෝගම
2019 නොවැම්බර් මස 30 දිනට අතැති බිල්පත් හා දෙසැම්බර් මස අපේක්ෂිත වියදම
(මූලධන වියදම් පමණක් ඇතුලත් කිරීම සදහා)
ශීර්ෂය(01) | ව්‍යාපෘතිය(02) | වැය විස්තරය(03) | 2019.11.30 දිනට අතැති බිල්පත් (04) රු. | 2019.දෙසැම්බර් මස සත්‍ය ලෙසම වැය කිරීමට බලාපොරොත්තුවන මුදල (05) | අපේක්ෂිත සම්පූර්ණ වියදම(04+05)
| සපිරි ගමක් ප්‍රජ සහභාගිත්ව සංවර්ධන වැඩසටහන |  |  | 1879860 | 1879860